## RAID Template
Item | RAID Category | Description | Risk Owner | Probability (P) | Impact (I) | Risk Score (P x I) | Current Status | Mitigation Strategy | Risk Reponse | Date Raised | Entered By | Key Updates | Date Closed
1 | Risk | Many moving parts and a fast build schedule - could step on each others’ toes | Rachel Collier | 3 | 4 | 12 | Closed | Staff teams, establish ceremonies, introduce governance series, open communication Channels | Treat/Reduction | 2026-01-02 | Rachel Collier | Monitor progress as Phase 2 gets started. Team can raise specific challenges if/when they arise and will be addressed. | 2026-02-27
2 | Risk | lack of feedback loop with every user persona: CRS Onco clinician payer provider (including provider’s admin assistant) patient configuration specialist | Caitlin Bowler | 4 | 3 | 12 | Closed | Define/Document UX Review Process | Treat/Reduction | 2026-01-02 | Rachel Collier | 3/6: Ux Design Review Process Document created, feedback received, and pending final approval. | 2026-03-06
3 | Risk | historical data migration: historical data too incomplete or messy to reconcile with new schema clients using the same field for different purposes difficulty adapting legacy reporting apparatus to new system (not much SDLC) | Erik Hjortshoj | 4 | 2 | 8 | In Progress | Review migration approach/drafted plan | Treat/Reduction | 2026-01-02 | Rachel Collier | 3/5: Design docs and migration plan being drafted. Need to determine if documents resolve risk items capatured. Historical data captured in another risk. Mtg request to update/define risk now with design docs drafted. Tgt w/o 3/2
4 | Risk | management of config insufficient testing of business rule combinations bad management of intersections between rulesets, leading to bad case states | Jack Hall | 4 | 4 | 16 | In Progress | Review/Approval on document Jack has developed. Reasses item after document gets approved. | Treat/Reduction | 2026-01-02 | Rachel Collier | 3/5: Jack has a doc that is being reviewed and if accepted should eliminate 3rd bullet and mitigate 2nd. Break apart. Mtg request to update/define risk now with design docs drafted. Tgt w/o 3/2
5 | Risk | reused peripheral services Matis and NewUM interfere with each other not enough service code gets exercised before cutover | Erik Hjortshoj | 4 | 3 | 12 | Open | Analysis meeting first | Treat/Reduction | 2026-01-02 | Rachel Collier | Break apart. Mtg request to update/define risk now with design docs drafted. Tgt w/o 3/2
6 | Decision | Use .NET WebAPI for API Gateway (decision based on feedback from Bogdan Chachun and Neal Ruggles) | Erik Hjortshoj |  |  | 0 | Closed |  |  | 2026-01-13 | Jack Hall | 2/27: Ask Jason to review/feedback. Email sent 3/3 update: Per Jason in email "Yes, .NET WebApi for the API gateway is recommended approach to handle our processes steadily. Agreed there." Closing Decision status | 2026-03-03
7 | Decision | Let OncoHealth handle the TaT service so that it integrates across NewUM, MATIS and SmartUM. Architec | Erik Hjortshoj |  |  | 0 | Closed |  |  | 2026-01-13 | Jack Hall | Related to #20. 2/27: Closing this item, reference item #20 going forward. | 2026-02-27
8 | Risk | New account provisioning for OncoHealth will take at least 5 days | Rachel Collier | 3 | 3 | 9 | Closed | Determine if Newfire can obtain email & phone 1 week in advance of "start" date to get the request in the queue and remove delays | Treat/Reduction | 2026-01-13 | Rachel Collier | Nearly all accounts are now provisioned for the project. Only a handful of resources are still to join the project and turnaround time has been quick. Closing the Risk 2/17 | 2026-02-17
9 | Risk | UX Schedule Research Delay | Alyssa Gessleman | 4 | 4 | 16 | Closed | First pass with Alison S. and Nichole C. during the rest of January. | Treat/Reduction | 2026-01-15 | Rachel Collier | Progress made; re-evaluate timeline/impact; 3/3: Resource availability from OH has improved along with end-user accessibility, no longer as risk as originally identified. | 2026-03-03
10 | Decision | Use DataDog for logging; OncoHealth considers AppInsights to be deprecated. | Erik Hjortshoj |  |  | 0 | Closed |  |  | 2026-01-21 | Jack Hall | Confirmed with Erik H. 2/27. Moving to Closed | 2026-02-27
11 | Risk | DevOps Environment Setup/ IDE | Rachel Collier | 3 | 3 | 9 | Closed | Itemize inventory of tools/apps by developer; complete by end of Feb | Treat/Reduction | 2026-01-22 | Rachel Collier | 2/27: All members have confirmed access with the exception of Matthew and Olha who's accts just got provisioned this week. They will work to confirm access and if any issues come up they will open a ticket to resolve. | 2026-02-27
12 | Risk | Work environments (Account provisoning) | Rachel Collier | 3 | 3 | 9 | Closed |  | Treat/Reduction | 2026-01-13 | Rachel Collier | Duplicate | 2026-01-29
13 | Decision | Do not use Automapper in .NET Entity Framework | Erik Hjortshoj |  |  | 0 | Closed |  | https://oncologyanalyticsinc-my.sharepoint.com/:w:/r/personal/jhall_oncologyanalytics_com/_layouts/15/Doc.aspx?sourcedoc=%7B447717B2-BE52-4C47-AE81-AD9FCC38A4A6%7D&file=Automapper%20or%20No.docx&action=default&mobileredirect=true&DefaultItemOpen=1&wdOrigin=WAC.WORD.HOME-BUTTON%2CAPPHOME-WEB.FILEBROWSER.RECENT&wdPreviousSession=ebc71ebf-660e-45eb-a477-b52e302885d9&wdPreviousSessionSrc=AppHomeWeb&ct=1769183354671 | 2026-01-23 | Jack Hall | 3/17: Per Donato it is not being used and can be closed. Donato checking with team (3/3) | 2026-03-17
14 | Risk | Databricks access is delayed another week | Vika Nobis | 5 | 4 | 20 | Closed | Raised in weekly onboarding meeting | Treat/Reduction | 2026-01-26 |  | 2/18: Confirmed with Vika, this is now closed. 1/28: oh-databricks-ws-test has been signed off by Marc as containing no PHI. Cleanup is in progress, and Databricks access is scheduled for 01/29 or 01/30 | 2026-02-18
15 | Risk | Miro Board access (all project team), limitation to 3 boards | Rachel Collier | 5 | 3 | 15 | Closed | team has been asked to stay inside NewUM board | Treat/Reduction | 2026-01-26 | Rachel Collier | 2/10: Closing risk. Licnenses have been upgraded, resources should now have access as needed. 1/28: License upgraded, team confirming. Ticket number 0032179 | 2026-02-10
16 | Risk | Core team experience with core prior auth and utilization management work flows could lead to longer cycles for BRD development and sign-off | Erik Hjortshoj | 5 | 4 | 20 | In Progress | Opportunity to engage external experts (case schema, workflows and configuration approach) | Treat/Reduction | 2026-01-27 | Sandy Gress | 3/13: Monitor going forward. Does not need review in RAID reviews. 2/27: noted Newfire is tapping one of advisors on schema design to have a few hours to work/review design
17 | Risk | Item 0 depends on sprint inputs and team capacity; shifts could delay 2/11 Review Package and 2/16 milestone | Alyssa Gessleman | 3 | 4 | 12 | Closed | Confirm owners, mid-sprint check-ins, early escalation | Treat/Reduction | 2026-02-04 | Alyssa Gessleman | Team presented the 2/16 milestone during the Sprint demo | 2026-02-17
18 | Risk | Delayed stakeholder feedback after 2/11 Review Package may cause rework and schedule compression | Alyssa Gessleman | 3 | 3 | 9 | Closed | Studio team to hold design critique with decision makers and document outcomes | Treat/Reduction | 2026-02-04 | Alyssa Gessleman | Feedback and approval provided. | 2026-02-17
19 | Assumption | Any Rules Engine will need to make some assumptions about what kinds of rules can be defined and how they execute. The attached doc contains our current knowledge of how this relates to architectural and business needs. | Erik Hjortshoj |  |  | 0 | Open |  | Rules Engine Edge Cases.docx | 2026-02-05 | Jack Hall
20 | Risk | TAT design evaluation (review/confirmation on go-forward) | Rachel Collier | 3 | 3 | 9 | In Progress | Develop fully functional reference | Treat/Reduction | 2026-02-10 | Rachel Collier | Action with Neal. 3/11: Confirmed with Neal, Solid progress so far, the team should have access to begin integration by 3/31; the timestamps generated may not be totally accurate but the results will start flowing through. Related to #7 Decision, keep one. 2/27: Keep. Fully functional reference due by 3/31. Donato/Neal/Matt have been in contact. An implementation call is to be scheduled.
21 | Risk | Recent spike in issues seen from Letters V2 (per Venky) | Erik Hjortshoj | 4 | 3 | 12 | Closed | Align/Confirm on recent spike resolution |  | 2026-02-10 | Rachel Collier | 2/20: project team mtg Neal stated spike in issues has trickled off. They had handled majority of the issues as a result of the content migration or content model migration. | 2026-02-27
22 | Risk | Dependency on final V1 scope and functional release definitions ahead of PI Planning for Ux sequencing/planning | Alyssa Gessleman | 3 | 4 | 12 | Closed | Review functional release draft early in the week; surface gaps and decisions quickly via the Decision Log | Treat/Reduction | 2026-02-17 | Alyssa Gessleman | Roadmap/functional releases received and reviewed; Questions raised and resolved with the Product team. UX/UI team planning and entering tickets. | 2026-02-23
23 | Risk | No direction about how much (if any) historical case information needs to be migrated from Matis -> NewUM. This is potentially a huge amount of work which needs to be addressed early in the project | Erik Hjortshoj | 2 | 3 | 6 | In Progress | The less that has to be migrated the better; balance that with business needs | Treat/Reduction | 2026-02-17 | Marc Gale | 3/6: draft doc uploaded to SP for review. 2/27: Task to schedule call (Donato) for next week so group can align on scenarios, risks and sequencing. 2/20: discussed in project team mtg. Next step is to identify first client (tgt end of Feb). Then team will need to regroup to determine approach. Will remain In Progress; update can be made after 1st client identified.
24 | Risk | Newfire data team wasn't aware of the shortcomings of OH's process of masking PHI. This had been noted several times in earlier meetings | Erik Hjortshoj | 2 | 3 | 6 | In Progress | Assess the work needed and plan for it | Treat/Reduction | 2026-02-17 | Marc Gale | 2/20: discussed in project team mtg. We owe designs that show where we're putting mock interfaces, where we're having to generate test data.
25 | Risk | Newfire had been working off the wrong diagram for provider schema. This results in rework for them after receiving the correct diagram | Erik Hjortshoj |  |  | 0 | Closed | Marc provided the schema (again) 2/17 | Treat/Reduction | 2026-02-17 | Marc Gale |  | 2026-02-17
26 | Risk | First testing client and first production client still unknown. Concerns that they may not be the same client. | Sandy Gress | 2 | 3 | 6 | Closed | Client list being generated by end of Feb. Next steps will include review and decision. Appropriate discussion and planning to take place after decision is made to determine impact. | Treat/Reduction | 2026-02-19 | Keeley Peck | 2/27: presentation on first Client (Sandy); #1 Geisinger, #2 Highmark Wholecare, #3 HealthPartners. Closing the risk now that identificatio has been made. 2/20: discussed in project team mtg, target end of Feb to identify 1st client | 2026-02-27
27 | Risk | Anterior impact (public API) | Erik Hjortshoj | 4 | 1 | 4 | On Hold | Requirements & Change Request decision |  | 2026-02-23 | Rachel Collier | 3/6: Venky noted team is about 2 weeks away from fully defining all the data elements that we are going to get. Evaluate when ready, determine if a Risk or a CR that needs to be created. Notes: expose public endpoints for our APIs for case entry and (2) we have to make sure there's the idea of provided-but-not-validated data so the CSR can approve the new case and validate the data provided
28 | Risk | BAs need to create 60 PRDs for R2 in preparation for the PI planning (2 per day) | Erik Hjortshoj | 5 | 4 | 20 | In Progress | Initiate Conf Specialist (BAs) role fulfillment earlier than planned. This is now in progress. | Treat/Reduction | 2026-02-27 | Vika Nobis | 3/18: Staffing being reviewed; additional project resources expected to support.
29 | Risk | Team needs to deliver 60 PRDs for R2 (2 per day). Taking into account results of 1st PI planning (8 for PI), this looks like risk | Erik Hjortshoj |  |  | 0 | Open | Dependency on item #28 |  | 2026-02-27 | Vika Nobis
30 | Decision | Project Team to confirm TAT functions correctly with NewUM. The functionality with SmartUM will be handled outside the Project Team |  |  |  | 0 | Closed |  |  | 2026-02-27 | Rachel Collier | Raised/documented during 2/27 prj mtg. | 2026-02-27
31 | Decision | Phase 1 Deliverable Date moved to March 13th | Rachel Collier |  |  | 0 | Closed |  |  | 2026-03-03 | Rachel Collier |  | 2026-03-03
32 | Decision | Use Postgres as an operational database for NewUM. | Donato Buccella |  |  |  | In Progress | waiting on exec sign-off |  | 2026-03-03 | Jack Hall | https://oncologyanalyticsinc-my.sharepoint.com/:w:/g/personal/jhall_oncologyanalytics_com/IQD0DSuZtNiXSa6uU3iYJNI7AdkBslIlyHhXlHPWDLdb_Pw?e=60ofzr
33 | Decision | Geisinger selected as first client for NewUM |  |  |  | 0 |  |  |  | 2026-02-27 | Rachel Collier | Sandy shared presentation at 2/27 meeting; team moving forward with decision. | 2026-03-04
34 |  | The test automation architecture and technology stack for both API and UI automation, shared on 3/11, does not clearly demonstrate alignment with OncoHealth’s expectations for a simple, maintainable, and supportable framework. OncoHealth is seeking a streamlined approach for API and UI automation that aligns with proven patterns and supports long‑term sustainability, scalability, and ease of adoption across teams. |  |  |  | 0 | On Hold |  |  | 2026-03-13 | Dimple Patel | 3/18: Per feedback from Venky, this item is deferred until mid April. A few sprints are needed to gain feedback. Follow up with next steps after 26.04.14 Sprint
35 |  | Configuration rework will potentially push the schedule out. | Erik Hjortshoj | 4 | 5 | 20 | In Progress |  |  | 2026-03-16 | Ann Dye
36 | [5 empty] | 0
37 | [5 empty] | 0
38 | [5 empty] | 0
39 | [5 empty] | 0
40 | [5 empty] | 0
41 | [5 empty] | 0
42 | [5 empty] | 0
43 | [5 empty] | 0
44 | [5 empty] | 0
45 | [5 empty] | 0
46 | [5 empty] | 0
47 | [5 empty] | 0
48 | [5 empty] | 0
49 | [5 empty] | 0
50 | [5 empty] | 0
51 | [5 empty] | 0
52 | [5 empty] | 0
53 | [5 empty] | 0
54 | [5 empty] | 0
55 | [5 empty] | 0
56 | [5 empty] | 0
57 | [5 empty] | 0
58 | [5 empty] | 0
59 | [5 empty] | 0
60 | [5 empty] | 0
61 | [5 empty] | 0
62 | [5 empty] | 0
63 | [5 empty] | 0
64 | [5 empty] | 0
65 | [5 empty] | 0
66 | [5 empty] | 0
67 | [5 empty] | 0
68 | [5 empty] | 0
69 | [5 empty] | 0
70 | [5 empty] | 0
71 | [5 empty] | 0
72 | [5 empty] | 0
73 | [5 empty] | 0
74 | [5 empty] | 0
75 | [5 empty] | 0
76 | [5 empty] | 0
77 | [5 empty] | 0
78 | [5 empty] | 0
79 | [5 empty] | 0
80 | [5 empty] | 0
81 | [5 empty] | 0
82 | [5 empty] | 0
83 | [5 empty] | 0
84 | [5 empty] | 0
85 | [5 empty] | 0
86 | [5 empty] | 0
87 | [5 empty] | 0
88 | [5 empty] | 0
89 | [5 empty] | 0
90 | [5 empty] | 0
91 | [5 empty] | 0
92 | [5 empty] | 0
93 | [5 empty] | 0
94 | [5 empty] | 0
95 | [5 empty] | 0
96 | [5 empty] | 0
97 | [5 empty] | 0
98 | [5 empty] | 0
99 | [5 empty] | 0
100 | [5 empty] | 0
30 | Issue | Product Team needs to review PRDs and provide input for #28. Limited resources | Sandy Gress | 5 | 5 | 25 | Open | Raising at 3/13 meeting |  | 2026-03-12 | Ann Dye | 3/12- Will discuss in weekly team call.
Note on I1: What will be done to reduce P or I or both -Rachel Collier
Note on L1: Rachel Collier: Populate with who entered the item

## Sign-Offs
Item/ Deliverable | Description | Version/ Artifact Link | Approver Name | Approval Method | Approval Status | Date Approved | Entered By | Notes
Case Intake Flow | Screens | Case Entry | Sandy Gress | Verbal: call on 3/9 | Approved | 2026-03-09 | Alyssa Gessleman | User_Testing_Log

## Definitions
For risks specifically, follow this 1-5 scoring system for Probability and Impact:
Probability (P): How likely is the risk to occur?
Score | Rating | Description
5 | Very High | Almost certain (70% - 100% chance)
4 | High | Likely to occur (50% - 70% chance)
3 | Medium | Possible (30% - 50% chance)
2 | Low | Unlikely (10% - 30% chance)
1 | Very Low | Rare chance (0% - 10% chance)
Impact (I): What is the severity if the risk occurs?
Score | Rating | Description
5 | Catastrophic | Project failure, major financial loss, legal penalties
4 | Severe | Significant schedule delay, budget overrun, serious reputation damage
3 | Moderate | Noticeable delay, moderate cost increase, minor disruption
2 | Minor | Slight delay, small cost increase, manageable inconvenience
1 | Negligible | Very little or no noticeable effect
Risk Score (P x I)
Score Range | Risk Level | Action Required
1 - 6 | Low | Monitor regularly.
7 - 14 | Medium | Define clear mitigation plans and review often.
15 - 25 | High | Prioritize immediate action, allocate resources, and track closely.
Current Status
Open
In Progress
On Hold
Closed
Risk Response
| Terminate/Avoidance | Eliminating the activity that gives rise to the risk
| Treat/Reduction | Implementing controls to reduce the likelihood or impact (e.g., security devices, training)
| Transfer/Sharing | Shifting the risk to another party (e.g., through insurance, outsourcing, or contracts)
| Tolerate/Acceptance | Acknowledging the risk and its potential impact, and budgeting for potential loss if the cost of treatment outweighs the cost of the risk
RAID Category | Risk | Is it a possibility? It’s a Risk.
Assumption
| Issue | Is it a reality? It’s an Issue
| Decision | Which way? Decision made between 2 or more alternatives
| Sign off | Formal Approval